## Tech Backlog
BACKLOG
Completion | Priority | EPIC | Task | Owner | Type | Estimation (h) | Planned Week
Not Started | 1 - Should Have |  | Batch Renderer | ym | Code | 10 | 6
Not Started | 1 - Should Have |  | Animation Component cleanup | ym/yx | Code |  | 4
Not Started | 1 - Should Have |  | Shader for effects | ym | Code | 12 | 6
Not Started | 1 - Should Have |  | Fix Lua Scripting | br | Code |  | 6
Not Started | 1 - Should Have |  | Animation system for editor | yx | Code |  | 4
Not Started | 1 - Should Have |  | Particle system | sy | Code | 24 | 4
In Progress | 0 - Must Have |  | Fix ¦ update Inspection | sy/yx | Code |  | 3
Not Started | 1 - Should Have |  | Camera system | ym | Code | 6 | 4
Done |  |  | Editor UI |  | Code
Done |  |  | Fix gizmo |  | Code
In Progress | 0 - Must Have |  | Fix Save of scene and prototype | sy/yx | Code |  | 3
In Progress | 0 - Must Have |  | Fix Add Component crashes | sy/yx | Code | 5 | 3
In Progress | 0 - Must Have |  | Fix lose of swtiching of Graphic image | sy/yx | Code | 5 | 3
In Progress | 0 - Must Have |  | editer camera | br | Code | 2 | 3
Not Started | 1 - Should Have |  | polygon collider component | sy | Code |  | 6
Not Started | 1 - Should Have |  | Audio Component | sy | Code |  | 4
Not Started | 1 - Should Have |  | Add on UI Component | ym/yx | Code | 6 | 6
Not Started | 2 - Could Have |  | Make Editor more user friendly | sy/yx | Code |  | 10
Not Started | 2 - Could Have |  | Play in edtitor mode | sy/yx | Code |  | 10
Not Started | 0 - Must Have |  | Correcting Old scripts | sy | Code |  | 3
Not Started | 0 - Must Have |  | Debug Old AI behaviour | br | Code
Done |  | Character |  |  | Code
In Progress |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
Not Started |  | Character |  |  | Code
In Progress |  | Combat |  |  | Code
Not Started |  | Combat |  |  | Code
Not Started |  | Combat |  |  | Code
Not Started |  | Combat |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
In Progress |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Not Started |  | Enemy AI |  |  | Code
Done |  | Music |  |  | Code
In Progress |  | Music |  |  | Code
Not Started |  | Music |  |  | Code
Not Started |  | Music |  |  | Code
Not Started |  | Music |  |  | Code
In Progress |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Props |  |  | Code
Not Started |  | Puzzle |  |  | Code
Not Started |  | Puzzle |  |  | Code
Not Started |  | Puzzle |  |  | Code
In Progress |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
Not Started |  | UI |  |  | Code
In Progress |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | World |  |  | Code
Not Started |  | Zones |  |  | Code
Note on E72: ====== ID#AAAAI3O_rGA Author (2020-01-19 05:38:40) Short sword, Long sword, Main hero sword
Note on E73: ====== ID#AAAAI3O_rF8 Author (2020-01-19 05:38:40) Small, big, Hero shield

## Design Backlog
BACKLOG
Completion | Priority | EPIC | Task | Owner | Type | Estimation (h) | Planned Week
In Progress | 0 - Must Have | Level | Level 1 Done | Boon Wee | Level Design | 5 | 3
Not Started | 0 - Must Have | Design | Feedback (In-game) |  | Other | 4 | 4
Done | 0 - Must Have | Playtesting | Update Playtest Scripts | Boon Wee | Other | 2 | 4
Not Started | 2 - Could Have | Documentation | GDD First Draft |  | Other | 2 | 8
Not Started | 0 - Must Have | Level | Level 2 Done | Harry | Level Design | 5 | 4
Not Started | 0 - Must Have | Scripting | Game Scripts, First Pass | Harry | Code |  | 4
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 1 - Should Have |  |  |  | Code
Done | 0 - Must Have |  |  |  | Code
Not Started | 1 - Should Have |  |  |  | Code
Not Started | 1 - Should Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Animation
Not Started | 1 - Should Have |  |  |  | Animation
Not Started | 1 - Should Have |  |  |  | Animation
Not Started | 1 - Should Have |  |  |  | Animation
Not Started | 0 - Must Have |  |  |  | Animation
Not Started | 0 - Must Have |  |  |  | Animation
Not Started | 0 - Must Have |  |  |  | Animation
Not Started | 0 - Must Have |  |  |  | Animation
Not Started | 0 - Must Have |  |  |  | Animation
Not Started | 0 - Must Have |  |  |  | Animation
Done | 0 - Must Have |  |  |  | Code
In Progress | 0 - Must Have |  |  |  | 3D Art
Not Started | 2 - Could Have |  |  |  | Animation
Not Started | 2 - Could Have |  |  |  | Animation
Not Started | 2 - Could Have |  |  |  | Animation
Not Started | 2 - Could Have |  |  |  | Animation
Not Started | 1 - Should Have |  |  |  | 3D Art
Not Started | 1 - Should Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | Animation
Not Started | 1 - Should Have |  |  |  | Code
In Progress | 0 - Must Have |  |  |  | Code
Not Started | 1 - Should Have |  |  |  | Code
Not Started | 1 - Should Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Code
In Progress | 0 - Must Have |  |  |  | Code
Not Started | 1 - Should Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Done | 0 - Must Have |  |  |  | Other
In Progress | 0 - Must Have |  |  |  | Other
Not Started | 1 - Should Have |  |  |  | Other
Not Started | 1 - Should Have |  |  |  | Other
Not Started | 1 - Should Have |  |  |  | Other
In Progress | 0 - Must Have |  |  |  | 3D Art
Not Started | 2 - Could Have |  |  |  | 3D Art
Not Started | 2 - Could Have |  |  |  | 3D Art
Not Started | 2 - Could Have |  |  |  | 3D Art
Not Started | 2 - Could Have |  |  |  | 3D Art
Not Started | 1 - Should Have |  |  |  | 3D Art
Not Started | 1 - Should Have |  |  |  | 3D Art
Not Started | 1 - Should Have |  |  |  | 3D Art
Not Started | 1 - Should Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 0 - Must Have |  |  |  | 3D Art
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
In Progress | 0 - Must Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Code
Not Started | 0 - Must Have |  |  |  | Other
Not Started | 0 - Must Have |  |  |  | Other
Not Started | 0 - Must Have |  |  |  | Other
Not Started | 0 - Must Have |  |  |  | Other
Not Started | 1 - Should Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Code
Not Started | 2 - Could Have |  |  |  | Other
Not Started | 2 - Could Have |  |  |  | Other
Not Started | 2 - Could Have |  |  |  | Other
Not Started | 2 - Could Have |  |  |  | Other
In Progress | 0 - Must Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Level Design
Not Started | 1 - Should Have |  |  |  | Level Design
Not Started | 0 - Must Have |  |  |  | Level Design
Not Started | 0 - Must Have |  |  |  | Level Design
Not Started | 0 - Must Have |  |  |  | Level Design
Not Started | 0 - Must Have |  |  |  | Level Design
Not Started | 2 - Could Have |  |  |  | Code

## Art Backlog
BACKLOG
Completion | Priority | EPIC | Task | Owner | Type | Estimation (h) | Planned Week
Done | 0 - Must Have | Level 1 Environment | Bounding walls props | Low Shao Xun | Other
Done | 1 - Must Have | Level 1 Environment | Props(obstacles) within the level | Low Shao Xun | Other
Done | 1 - Should Have | Level 1 Environment | Texture props | Low Shao Xun | Other
Done | 0 - Must Have | Level 1 Animation | Atmospheric animation (Smoke, electric sparks) | Low Shao Xun | Other
Done | 4 - Must Have | Character Animation | Body hovering | Low Shao Xun | Other
Done | 5 - Must Have | Character Animation | Muzzle movement for shooting | Low Shao Xun | Other
Done | 2 - Could Have | Character Animation | Electric current coursing around the body | Low Shao Xun | Other
Not Started | 0 - Must Have | Character Animation | Damaged animation | Low Shao Xun | Other
Not Started | 0 - Must Have | Character Animation | Death animation | Low Shao Xun | Other
Done | 1 - Should Have | Turret Animation | Transformation of turret when summoned | Low Shao Xun | Other
Done | 8 - Must Have | Turret Animation | Shooting direction of the turret | Low Shao Xun | Other
Done | 9 - Must Have | Enemy Animation | movements | Low Shao Xun | Other
Not Started | 0 - Must Have | Enemy Animation | Damaged animation | Low Shao Xun | Other
In Progress | 10 - Must Have | Enemy Animation | Death animation | Low Shao Xun | Other
Done | 11 - Must Have | Powers and effect | Bullets and power ups | Low Shao Xun | Other
Done | 1 - Should Have | UI | Starting screen | Low Shao Xun | Other
Done | 0 - Must Have | UI | HP bar | Low Shao Xun | Other
In Progress | 0 - Must Have | UI | Buttons and menu | Low Shao Xun | Other
Not Started | 0 - Must Have | Character |  |  | Animation
Not Started | 0 - Must Have | Character |  |  | Animation
Not Started | 0 - Must Have | Character |  |  | Animation
Not Started | 0 - Must Have | Character |  |  | Animation
Not Started | 0 - Must Have | Character |  |  | Animation
Not Started | 0 - Must Have | Character |  |  | Animation
Done | 0 - Must Have | Character |  |  | Code
In Progress | 0 - Must Have | Character |  |  | 3D Art
Not Started | 2 - Could Have | Character |  |  | Animation
Not Started | 2 - Could Have | Character |  |  | Animation
Not Started | 2 - Could Have | Character |  |  | Animation
Not Started | 2 - Could Have | Character |  |  | Animation
Not Started | 1 - Should Have | Character |  |  | 3D Art
Not Started | 1 - Should Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | 3D Art
Not Started | 0 - Must Have | Character |  |  | Animation
Not Started | 1 - Should Have | Character |  |  | Code
In Progress | 0 - Must Have | Combat |  |  | Code
Not Started | 1 - Should Have | Combat |  |  | Code
Not Started | 1 - Should Have | Combat |  |  | Code
Not Started | 0 - Must Have | Combat |  |  | Code
Not Started | 2 - Could Have | Enemy AI |  |  | Code
Not Started | 2 - Could Have | Enemy AI |  |  | Code
Not Started | 2 - Could Have | Enemy AI |  |  | Code
Not Started | 0 - Must Have | Enemy AI |  |  | Code
Not Started | 0 - Must Have | Enemy AI |  |  | Code
Not Started | 0 - Must Have | Enemy AI |  |  | Code
In Progress | 0 - Must Have | Enemy AI |  |  | Code
Not Started | 1 - Should Have | Enemy AI |  |  | Code
Not Started | 2 - Could Have | Enemy AI |  |  | Code
Not Started | 2 - Could Have | Enemy AI |  |  | Code
Done | 0 - Must Have | Music |  |  | Other
In Progress | 0 - Must Have | Music |  |  | Other
Not Started | 1 - Should Have | Music |  |  | Other
Not Started | 1 - Should Have | Music |  |  | Other
Not Started | 1 - Should Have | Music |  |  | Other
In Progress | 0 - Must Have | Props |  |  | 3D Art
Not Started | 2 - Could Have | Props |  |  | 3D Art
Not Started | 2 - Could Have | Props |  |  | 3D Art
Not Started | 2 - Could Have | Props |  |  | 3D Art
Not Started | 2 - Could Have | Props |  |  | 3D Art
Not Started | 1 - Should Have | Props |  |  | 3D Art
Not Started | 1 - Should Have | Props |  |  | 3D Art
Not Started | 1 - Should Have | Props |  |  | 3D Art
Not Started | 1 - Should Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 0 - Must Have | Props |  |  | 3D Art
Not Started | 2 - Could Have | Puzzle |  |  | Code
Not Started | 2 - Could Have | Puzzle |  |  | Code
Not Started | 2 - Could Have | Puzzle |  |  | Code
In Progress | 0 - Must Have | UI |  |  | Code
Not Started | 0 - Must Have | UI |  |  | Code
Not Started | 0 - Must Have | UI |  |  | Code
Not Started | 0 - Must Have | UI |  |  | Other
Not Started | 0 - Must Have | UI |  |  | Other
Not Started | 0 - Must Have | UI |  |  | Other
Not Started | 0 - Must Have | UI |  |  | Other
Not Started | 1 - Should Have | UI |  |  | Code
Not Started | 2 - Could Have | UI |  |  | Code
Not Started | 2 - Could Have | UI |  |  | Code
Not Started | 2 - Could Have | UI |  |  | Code
Not Started | 2 - Could Have | UI |  |  | Other
Not Started | 2 - Could Have | UI |  |  | Other
Not Started | 2 - Could Have | UI |  |  | Other
Not Started | 2 - Could Have | UI |  |  | Other
In Progress | 0 - Must Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 2 - Could Have | World |  |  | Level Design
Not Started | 1 - Should Have | World |  |  | Level Design
Not Started | 0 - Must Have | World |  |  | Level Design
Not Started | 0 - Must Have | World |  |  | Level Design
Not Started | 0 - Must Have | World |  |  | Level Design
Not Started | 0 - Must Have | World |  |  | Level Design
Not Started | 2 - Could Have | Zones |  |  | Code

## Project Stats
[12 empty] | Completion | Not Started
Total Workload |  |  |  |  | Total Workload by Milestone
Sum of Estimation (h) | Completion |  |  |  | Sum of Estimation (h) | Planned Week | [5 empty] | Sum of Estimation (h) | Planned Week
Owner | Done | In Progress | Not Started | Grand Total | Owner | 3 | 4 | 6 | 10 | (blank) | Grand Total | Owner | 4 | 6 | 10 | (blank) | Grand Total
br |  | 2 |  | 2 | br | 2 |  |  |  |  | 2 | br
sy |  |  | 24 | 24 | sy |  | 24 |  |  |  | 24 | sy | 24 |  |  |  | 24
sy/yx |  | 10 |  | 10 | sy/yx | 10 |  |  |  |  | 10 | sy/yx
ym |  |  | 28 | 28 | ym |  | 6 | 22 |  |  | 28 | ym | 6 | 22 |  |  | 28
ym/yx |  |  | 6 | 6 | ym/yx |  |  | 6 |  |  | 6 | ym/yx |  | 6 |  |  | 6
yx |  |  |  |  | yx | [6 empty] | yx
(blank) |  |  |  |  | (blank) | [6 empty] | (blank)
Grand Total |  | 12 | 58 | 70 | Grand Total | 12 | 30 | 28 |  |  | 70 | Grand Total | 30 | 28 |  |  | 58
Available Time
Length of project |  | 14 | Weeks
Average Availability : |  | 16 | Hours / Week
Size of Team |  | 7 | Members
|  | 1568 | Total Available Hours
Project stats
Total VS Available Time : |  |  | 4.464%
Total Completion Rate: |  |  | 0%

## Style
Completion | Priority | Task Type | Who | What | Percent
Not Started | 0 - Must Have | 3D Art | Yimin | Code | 0%
In Progress | 1 - Should Have | Animation | Brandon | Code | 75%
Done | 2 - Could Have | Code | Shu Yu | Code | 150%
| 3 - Won't Have | Level Design | Yu Xuan | Code
|  | Other | Harry | Level Design
|  |  | Boon Wee | Level Design
|  |  | Shao Xun | Art
|  |  | Shao Xun | Animation